## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Overview of the project(MediTrain AI - Empowering the Doctors of Tomorrow, Today | MUST HAVE | NoDependencies | Mentor-506 | 3- Completed
S1 | S1 | US-002 | Workflow creation and project goal document | MUST HAVE | Charts | Mentor-506 | 3- Completed
S2 | S2 | US-003 | Document discussion(Agile Template,Defect Tracker,Unit Testing) | MUST HAVE | Excel sheets | Mentor-506 | 3- Completed
S2 | S2 | US-004 | Use Case Research and Preparation | SHOULD HAVE | W3 Schools, Dribble and Docs | Mentor-506 | 3- Completed
S3 | S3 | US-005 | Python practice kit completion | MUST HAVE | Hacker Rank | Mentor-506 | 3- Completed
S4 | S4 | US-006 | Langchain,Flask, Prompts kit completion | MUST HAVE | Documentations | Mentor-506 | 3- Completed
S5 | S5 | US-007 | Project Discussion Module 1(Language Processing) | MUST HAVE | Groq API | Mentor-506 | 3- Completed
S6 | S6 | US-008 | Project Discussion Module 2(Workflow Efficiency) | SHOULD HAVE | VS Code | Mentor-506 | 3- Completed
S7 | S7 | US-009 | Project Discussion Module 3(Merging Existing Services) | SHOULD HAVE | Langchain/bs4 | Mentor-506 | 3- Completed
S8 | S8 | US-010 | Project Discussion Module 4(Testing and Deployment) | COULD HAVE | Render/Netlify | Mentor-506 | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 53 | 15 | 13 | 8 | 8 | 4 | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-1 | TID-1 | Overview of the project(MediTrain AI) | 2024-11-04 | 2024-11-06 |  | Others | 3-Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-2 | TID-2 | Workflow creation and project goal document | 2024-11-07 | 2024-11-08 |  | Design | 3-Completed | 4 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-3 | TID-3 | Document discussion(Agile Template,Defect Tracker,Unit Testing) | 2024-11-11 | 2024-11-11 |  | Others | 3-Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-4 | TID-4 | Python practice kit completion | 2024-11-12 | 2024-11-14 |  | Others | 3-Completed | 4 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-5 | TID-5 | Langchain,Flask, Prompts kit completion | 2024-11-16 | 2024-11-18 |  | Coding | 3-Completed | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-7 | TID-6 | Project Discussion Module 1(Language Processing) | 2024-12-02 | 2024-12-05 |  | Build | 3-Completed | 9 | 2 | 1 | 2 | 2 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-8 | TID-7 | Project Discussion Module 2(Workflow Efficiency) | 2024-12-09 | 2024-12-14 |  | Coding | 3-Completed | 6 | 2 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-9 | TID-8 | Project Discussion Module 3(Merging Existing Services) | 2024-12-15 | 2024-12-21 |  | Integration Test | 3-Completed | 10 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | TID-9 | Project Discussion Module 4(Testing and Deployment) | 2024-12-23 | 2024-12-26 |  | System Test | 3-Completed | 11 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 3 | Day 12 | Different user personas | User grooming sessions were conducted
Sprint 5 | Day 24 | Agile Template Confusion | conducted a meeting where all doubts were clear by the mentor
Sprint 6 | Day 26 | Lack of clarity with enviornment files and containerized deployments | conducted a meeting where all doubts were clear by the mentor
sprint 7 | Day 29 | Confusion in integrtaing LMS | Consulted with mentor to resolve the issue.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 6 | 2024-11-15 | 2024-11-22 |  |  | pushing env file | specific env file according to the environment | Using env.local, adding example env for ease
2 | Sprint 7 | 2024-12-15 | 2024-12-20 |  |  | using paid API'S | Exploring different LLM'S | Found a LLM that will be great for the chatbot
3
4
5
6
7